## Sheet1
Product Name | Shikho (Mobile App) | TC Start Date | 2022-01-27 |  | TC Execution Start Date | 2022-01-27 | TEST CASE SUMMARY
Module Name | All Modules | TC End Date | 2022-01-28 |  | TC Execution End Date | 2022-01-28 | PASS | 14
|  | Test Case Developed By |  | Madhurjo Das Aishy | Browser (tested) | 1 | FAIL | 5
Version | 1.0.8 | Test Case Reviewed By |  | M | Performance (tested) | No | WARNING | 0
Test Executed by |  | Madhurjo Das Aishy |  |  |  |  | TOTAL | 19
Bug#ID | Module Name | Build No | Description | TCID | Steps to replicate bug | Screen Shot | Severity | Priority | Remarks
Bug_ID__001 | Profile Update | V-1.0.8 | after uploading profile picture successfully, 'provide correct email address' message pops up. | SIKHO-T7 | Go to edit profile Upload profile pic | SS | S3 | P3
Bug_ID__002 | Profile Update | V-1.0.8 | after giving correct email address no email verification is done. | SIKHO-T9 | Go to edit profile Update email address with valid email |  | S2 | P2
Bug_ID__003 | Profile Update | V-1.0.8 | after giving non existing email address no email verification is done. It is still accepted | SIKHO-T11 | Go to edit profile Update email address with non existing email | SS | S2 | P2
Bug_ID__004 | Profile Update | V-1.0.8 | In father's name, mother's name section invalid names are getting accepted | SIKHO-T13 | Go to edit profile Update Father's name, Mother's name with numbers and special characters | SS | S3 | P3
Bug_ID__005 | Profile Update | V-1.0.8 | After giving invalid characters such as numbers and special characters in name it is still being accepted | SIKHO-T13 | Go to edit profile Update your name with numbers and special characters | SS | S3 | P3